## Sheet1
Burndown Chart
User story | Start Hours | Hours spent - day 1 | Hours spent - day 2 | Hours spent - day 3 | Total hours
8. As a customer, I want to be able to log in as a customer, so that I can access the airline reservation system. | 6 | 1 | 4 | 1 | 6
15. As an operator, I want to log in as an operator, so that I can access the airline reservation system. | 7 | 3 | 2 | 2 | 7
7. As a customer, I want to register myself as a customer, so that I can use the airline reservation system. | 12 | 3 | 2 | 7 | 12
12. As an operator, I want to create flights, so that the customers can view them. | 13 | 8 | 2 | 3 | 13
3. As a customer, I want to view available flights, so that I can book my preferred flights. | 15 | 5 | 5 | 5 | 15
4. As a customer, I want to choose the date of the flights, so that I can reach my destination in my desired date. | 7 | 6 | 0 | 1 | 7
17. As a customer, I want to search for specific flights by their destination, so that I can narrow my flight search. | 12 | 0 | 5 | 7 | 12
19. As a customer, I want the option to buy additional luggage, so that I can bring more luggage to the flight. | 20 | 10 | 2 | 8 | 20
1. As a customer, I want to book flights, so that I can fly to my destination. | 20 | 4 | 5 | 11 | 20
2. As a customer, I want reserve seats on flights, so that I can sit on the favoured seat in the flight. | 25 | 6 | 7 | 12 | 25
18. As a customer, I want to view the details of the flights such as the destination, time taken and date, so that I know the details of the flight I am about to book. | 8 | 1 | 5 | 2 | 8
9. As a customer, I want to view my booked flights, so that I know which flights I have booked. | 12 | 2 | 4 | 6 | 12
6. As a customer, I want to be able to view the status of my booked flights, so that I will know the status of my booked flights. | 10 | 5 | 2 | 3 | 10
5. As a customer, I want to be notified when my booked flights get delayed or cancelled, so that I will be aware of it. | 5 | 0 | 0 | 5 | 5
13. As an operator, I want to edit the flight information on existing flights, so that the customers can have the latest flight information. | 14 | 4 | 4 | 6 | 14
14. As an operator, I want to cancel flights, so that the cancelled flights will be removed and customers who have booked the cancelled flights will be notified. | 15 | 2 | 6 | 7 | 15
20. As an operator, I want to delay flights, so that customers will be able to check whether their flights are delayed. | 10 | 2 | 2 | 6 | 10
22. As a customer, I want to edit my user info, so that it is updated. | 4 | 0 | 0 | 4 | 4
23. As a customer, I want to view my name when I log in, so that I can identify if I have logged into my account. | 1 | 0 | 0 | 1 | 1
24. As a customer, I want to view the previous flights that I have taken, so that I can look up which flights I have taken. | 5 | 5 | 0 | 0 | 5
Actual hours remaining | 221 | 154 | 97 | 0
Estimated hours remaining | 221 | 147.3333 | 73.6667 | 0